## 02-stories
# | Issue key | Issue id | Custom field (Epic Link) | Ename | Assignee | Custom field (Story Points) | teste | Original Estimate | Time Spent | Remaining Estimate | Sprint | Sprint2 | Sprint3 | Summary
1 | PCS-28233 | 596065 | PCS-28016 | May21-21xPCS | ssubramanian | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | [ISA8K]: System is allowing more than permitted Licenses
2 | PCS-28264 | 596185 | PCS-28016 | May21-21xPCS | ssubramanian | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | [ISA8K-F]:Able to establish 25K Tunnels without licenses
3 | PCS-28333 | 596498 | PCS-28322 | May21-New Platform support | ssubramanian | 6 |  | 86400 | 86400 | 0 | PCS-2124 |  |  | ISA8K Platform porting document-part1
4 | PCS-27371 | 592012 | PCS-28322 | May21-New Platform support | ssubramanian | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | SM HW: Licensing Dev Information Documentation
5 | PCS-27022 | 590514 | PCS-28017 | May21-Deployment-Phase2 | rajeshg | 6 |  | 86400 | 64800 | 21600 | PCS-2118 | PCS-2120 | PCS-2124 | SuperDoctor: Confirm SuperDoctor diagnostic tool with SM-HW port
6 | PCS-28232 | 596064 | PCS-28017 | May21-Deployment-Phase2 | rajeshg | 4 |  | 57600 | 115200 | 0 | PCS-2124 |  |  | [ISA8K]: HW status & other information missing from Admin UI
7 | PCS-28332 | 596496 | PCS-28017 | May21-Deployment-Phase2 | rajeshg | 6 |  | 86400 | 10800 | 75600 | PCS-2124 | PCS-2126 |  | SM-HW: Pixe Packaging - Testing on HW
8 | PCS-28312 | 596429 | PCS-28311 | May21-Baseline | praveens | 4 |  | 57600 | 115200 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(ESP)
9 | PCS-28318 | 596435 | PCS-28311 | May21-Baseline | praveens | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(ESP)
10 | PCS-28319 | 596436 | PCS-28311 | May21-Baseline | praveens | 6 |  | 86400 | 86400 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(ESP)
11 | PCS-28441 | 596948 | PCS-28322 | May21-New Platform support | praveens | 2 |  | 28800 | 50400 | 0 | PCS-2124 |  |  | [SM-HW]: Investigate the issue where admin UI is not accessible on HW 38
12 | PCS-28313 | 596430 | PCS-28311 | May21-Baseline | karthikr | 4 |  | 7200 | 115200 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(SSL)
13 | PCS-28315 | 596432 | PCS-28311 | May21-Baseline | karthikr | 6 |  | 86400 | 28800 | 0 | PCS-2124 | PCS-2126 |  | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(SSL)
14 | PCS-26807 | 589433 | PCS-28017 | May21-Deployment-Phase2 | kalaimani.k | 8 |  | 115200 | 28800 | 0 | PCS-2114 | PCS-2124 |  | SMHW: Checking BIOS configuration
15 | PCS-28334 | 596499 | PCS-28322 | May21-New Platform support | kalaimani.k | 6 |  | 86400 | 172800 | 0 | PCS-2124 |  |  | ISA8K Platform porting document (Driver related)
16 | PCS-28663 | 597761 | PCS-28322 | May21-New Platform support | kalaimani.k | 4 |  | 1200 | 57600 | 0 | PCS-2124 |  |  | SM-HW: Analysis and Explore the Secure Boot option on SM HW
17 | PCS-28355 | 596647 | PCS-28016 | May21-21xPCS | balajit | 6 |  | 86400 | 104400 | 0 | PCS-2124 |  |  | SM-HW: ISA8000 License parameters information collection
18 | PCS-28357 | 596652 | PCS-28016 | May21-21xPCS | balajit | 6 |  | 86400 | 57600 | 28800 | PCS-2124 |  |  | SM HW: CPU Affinity Usage Checking during traffic
19 | PCS-28390 | 596746 | PCS-28016 | May21-21xPCS | balajit | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | SM-HW: ISA8000 License checking support
20 | PCS-28314 | 596431 | PCS-28311 | May21-Baseline | balachandras | 6 |  | 86400 | 57600 | 0 | PCS-2124 | PCS-2126 |  | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(SSL)
21 | PCS-28316 | 596433 | PCS-28311 | May21-Baseline | balachandras | 8 |  | 14400 | 144000 | 0 | PCS-2124 | PCS-2126 |  | QA-ISA8K-Perf Baseline: Throughput-Standard/less packet sizes/varied user load(SSL)
22 | PCS-28438 | 596940 | PCS-28322 | May21-New Platform support | balachandras | 2 |  | 28800 | 57600 | 0 | PCS-2124 |  |  | [SM HW]: Flashing serial number to BIOS

## 01-epics
# | Custom field (Epic Link) | Ename | ESdate | ETdate | EASDate | EAEDate
1 | PCS-28018 | May21-Performance | 2021-05-20 | 2021-06-17 | 2021-05-20 | 2021-06-17
2 | PCS-28042 | May21-ISA8000x-Support | 2021-05-20 | 2021-06-03 | 2021-05-20 | 2021-06-03
3 | PCS-28017 | May21-Deployment-Phase2 | 2021-05-20 | 2021-06-03 | 2021-05-20 | 2021-06-03
4 | PCS-28016 | May21-21xPCS | 2021-05-20 | 2021-06-17 | 2021-05-20 | 2021-06-17
5 | PCS-28322 | May21-New Platform support | 2021-05-20 | 2021-06-17 | 2021-05-20 | 2021-06-17
6 | PCS-28311 | May21-Baseline | 2021-05-04 | 2021-07-13 | 2021-05-04 | 2021-06-17

## epics_stories
SPRINT/STORY BOARD
# | EPIC ID | SPRINT ID | STORY ID | STORY DESCRIPTION | ASSIGNED TO | ESTIMATED STORY POINTS | STORY PLANNED START | STORY PLANNED END | ESTIMATED EFFORT (IN HRS)) | Time spent (IN Secs) | EFFORT CONSUMED (IN HRS) | PENDING EFFORT (IN HRS) | STORY ACTUAL START | STORY ACTUAL END | STORY Effort completion % | STORY Schedule Progress % | STORY Schedule Overrun % | Remarks
1 | PCS-28016 | PCS-2124 | PCS-28233 | [ISA8K]: System is allowing more than permitted Licenses | ssubramanian | 4 | 2021-05-20 | 2021-06-17 | 16 | 57600 | 16 | 0 | 2021-05-20 | 2021-06-17 | 100 | 100% | 0%
2 | PCS-28016 | PCS-2124 | PCS-28264 | [ISA8K-F]:Able to establish 25K Tunnels without licenses | ssubramanian | 4 | 2021-05-20 | 2021-06-17 | 16 | 57600 | 16 | 0 | 2021-05-20 | 2021-06-17 | 100 | 100% | 0%
3 | PCS-28322 | PCS-2124 | PCS-28333 | ISA8K Platform porting document-part1 | ssubramanian | 6 | 2021-05-20 | 2021-06-17 | 24 | 86400 | 24 | 0 | 2021-05-20 | 2021-06-17 | 100 | 100% | 0%
4 | PCS-28322 | PCS-2124 | PCS-27371 | SM HW: Licensing Dev Information Documentation | ssubramanian | 4 | 2021-05-20 | 2021-06-17 | 16 | 57600 | 16 | 0 | 2021-05-20 | 2021-06-17 | 100 | 100% | 0%
5 | PCS-28017 | PCS-2124 | PCS-27022 | SuperDoctor: Confirm SuperDoctor diagnostic tool with SM-HW port | rajeshg | 6 | 2021-05-20 | 2021-06-03 | 24 | 64800 | 18 | 6 | 2021-05-20 | 2021-06-03 | 133.3333 | 100% | 0%
6 | PCS-28017 | PCS-2124 | PCS-28232 | [ISA8K]: HW status & other information missing from Admin UI | rajeshg | 4 | 2021-05-20 | 2021-06-03 | 16 | 115200 | 32 | -16 | 2021-05-20 | 2021-06-03 | 50 | 100% | 0%
7 | PCS-28017 | PCS-2126 | PCS-28332 | SM-HW: Pixe Packaging - Testing on HW | rajeshg | 6 | 2021-05-20 | 2021-06-03 | 24 | 10800 | 3 | 21 | 2021-05-20 | 2021-06-03 | 800 | 100% | 0%
8 | PCS-28311 | PCS-2124 | PCS-28312 | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(ESP) | praveens | 4 | 2021-05-04 | 2021-07-13 | 16 | 115200 | 32 | -16 | 2021-05-04 | 2021-06-17 | 50 | 100% | 0%
9 | PCS-28311 | PCS-2124 | PCS-28318 | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(ESP) | praveens | 4 | 2021-05-04 | 2021-07-13 | 16 | 57600 | 16 | 0 | 2021-05-04 | 2021-06-17 | 100 | 100% | 0%
10 | PCS-28311 | PCS-2124 | PCS-28319 | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(ESP) | praveens | 6 | 2021-05-04 | 2021-07-13 | 24 | 86400 | 24 | 0 | 2021-05-04 | 2021-06-17 | 100 | 100% | 0%
11 | PCS-28322 | PCS-2124 | PCS-28441 | [SM-HW]: Investigate the issue where admin UI is not accessible on HW 38 | praveens | 2 | 2021-05-20 | 2021-06-17 | 8 | 50400 | 14 | -6 | 2021-05-20 | 2021-06-17 | 57.1429 | 100% | 0%
12 | PCS-28311 | PCS-2124 | PCS-28313 | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(SSL) | karthikr | 4 | 2021-05-04 | 2021-07-13 | 2 | 115200 | 32 | -30 | 2021-05-04 | 2021-06-17 | 6.25 | 100% | 0%
13 | PCS-28311 | PCS-2126 | PCS-28315 | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(SSL) | karthikr | 6 | 2021-05-04 | 2021-07-13 | 24 | 28800 | 8 | 16 | 2021-05-04 | 2021-06-17 | 300 | 100% | 0%
14 | PCS-28017 | PCS-2124 | PCS-26807 | SMHW: Checking BIOS configuration | kalaimani.k | 8 | 2021-05-20 | 2021-06-03 | 32 | 28800 | 8 | 24 | 2021-05-20 | 2021-06-03 | 400 | 100% | 0%
15 | PCS-28322 | PCS-2124 | PCS-28334 | ISA8K Platform porting document (Driver related) | kalaimani.k | 6 | 2021-05-20 | 2021-06-17 | 24 | 172800 | 48 | -24 | 2021-05-20 | 2021-06-17 | 50 | 100% | 0%
16 | PCS-28322 | PCS-2124 | PCS-28663 | SM-HW: Analysis and Explore the Secure Boot option on SM HW | kalaimani.k | 4 | 2021-05-20 | 2021-06-17 | 0.33333 | 57600 | 16 | -16 | 2021-05-20 | 2021-06-17 | 0 | 100% | 0%
17 | PCS-28016 | PCS-2124 | PCS-28355 | SM-HW: ISA8000 License parameters information collection | balajit | 6 | 2021-05-20 | 2021-06-17 | 24 | 104400 | 29 | -5 | 2021-05-20 | 2021-06-17 | 82.7586 | 100% | 0%
18 | PCS-28016 | PCS-2124 | PCS-28357 | SM HW: CPU Affinity Usage Checking during traffic | balajit | 6 | 2021-05-20 | 2021-06-17 | 24 | 57600 | 16 | 8 | 2021-05-20 | 2021-06-17 | 150 | 100% | 0%
19 | PCS-28016 | PCS-2124 | PCS-28390 | SM-HW: ISA8000 License checking support | balajit | 4 | 2021-05-20 | 2021-06-17 | 16 | 57600 | 16 | 0 | 2021-05-20 | 2021-06-17 | 100 | 100% | 0%
20 | PCS-28311 | PCS-2126 | PCS-28314 | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(SSL) | balachandras | 6 | 2021-05-04 | 2021-07-13 | 24 | 57600 | 16 | 8 | 2021-05-04 | 2021-06-17 | 150 | 100% | 0%
21 | PCS-28311 | PCS-2126 | PCS-28316 | QA-ISA8K-Perf Baseline: Throughput-Standard/less packet sizes/varied user load(SSL) | balachandras | 8 | 2021-05-04 | 2021-07-13 | 4 | 144000 | 40 | -36 | 2021-05-04 | 2021-06-17 | 10 | 100% | 0%
22 | PCS-28322 | PCS-2124 | PCS-28438 | [SM HW]: Flashing serial number to BIOS | balachandras | 2 | 2021-05-20 | 2021-06-17 | 8 | 57600 | 16 | -8 | 2021-05-20 | 2021-06-17 | 50 | 100% | 0%