## 01-epics
# | Custom field (Epic Link) | Ename | ESdate | ETdate | EASDate | EAEDate
1 | PCS-28018 | May21-Performance | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021
2 | PCS-28042 | May21-ISA8000x-Support | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06
3 | PCS-28017 | May21-Deployment-Phase2 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06

## 02-stories
s.no | Issue key | Issue id | Custom field (Epic Link) | Ename | Assignee | Custom field (Story Points) | Original Estimate | Time Spent | Remaining Estimate | Sprint | Sprint2 | Sprint3 | Summary
1 | PCS-27974 | 594882 | PCS-28018 | May21-Performance | balachandras |  | 57600 | 0 | 57600 | PCS-2122 |  |  | QA: Testing the throughput with standard/less packet sizes/varied user load in ESP mode
2 | PCS-27972 | 594870 | PCS-28018 | May21-Performance | balachandras | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | QA:SM HW : ESP Max Users/Tunnel Setup count
3 | PCS-27539 | 593251 | PCS-28018 | May21-Performance | balachandras | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | Planning to validate RAID and LVM testing
4 | PCS-25735 | 583642 | PCS-28018 | May21-Performance | balachandras | 4 | 57600 | 43200 | 57600 | PCS-2122 | PCS-2112 |  | QA: Testing the HW-RAID controller functionality
5 | PCS-28004 | 594947 | PCS-28042 | May21-ISA8000x-Support | balajit | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | SM HW - ISA8000F Platform Testing, Code Review
6 | PCS-28003 | 594946 | PCS-28042 | May21-ISA8000x-Support | balajit | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | SM HW - ISA8000F Platform addition - License and UI Changes
7 | PCS-28002 | 594945 | PCS-28042 | May21-ISA8000x-Support | balajit | 6 | 86400 | 82800 | 3600 | PCS-2122 |  |  | SM HW - ISA8000F Platform addition - Platform changes
8 | PCS-27971 | 594869 | PCS-28017 | May21-Deployment-Phase2 | kalaimani.k | 4 | 57600 | 57600 | 0 | PCS-2122 |  |  | SM-HW : ISA8000 - Make Coreboot/init changes as platform specific
9 | PCS-27007 | 590473 | PCS-28017 | May21-Deployment-Phase2 | kalaimani.k | 8 | 115200 | 28800 | 86400 | PCS-2118 | PCS-2120 | PCS-2122 | SM-HW: ISA8000 Upgrade and Rollover Confirmation with LVM
10 | PCS-27969 | 594853 | PCS-28017 | May21-Deployment-Phase2 | kalaimani.k | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | LVM: Support and bug fixes
11 | PCS-27566 | 593427 | PCS-28018 | May21-Performance | karthikr | 4 | 28800 | 0 | 28800 | PCS-2122 |  |  | QA: SMHW: Tunnel setup rate test for 25k Users on SSL mode
12 | PCS-27538 | 593250 | PCS-28018 | May21-Performance | karthikr | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | QA: SM HW : Perform throughput tests with IMIX traffic(SSL)
13 | PCS-27978 | 594893 | PCS-28018 | May21-Performance | karthikr | 4 | 57600 | 0 | 57600 | PCS-2122 |  |  | QA: SM HW : SSL Max Throughput (25k Users/Tunnels, 1350 bytes)
14 | PCS-27975 | 594885 | PCS-28018 | May21-Performance | karthikr | 2 | 28800 | 14400 | 14400 | PCS-2122 |  |  | QA: Build image from Build plan

## epic_stories
s.no | STORY ID | Issue id | EPIC ID | STORY PLANNED START | STORY PLANNED END | STORY ACTUAL START | STORY ACTUAL END | Ename | ASSIGNED TO | STORY Effort completion % | ESTIMATED STORY POINTS | Time spent (IN Secs) | EFFORT CONSUMED (IN HRS) | Time Spent | ESTIMATED EFFORT (IN HRS)) | Remaining Estimate | PENDING EFFORT (IN HRS) | SPRINT ID | Sprint2 | Sprint3 | STORY Schedule Progress % | STORY Schedule Overrun % | Remarks | STORY DESCRIPTION
1 | PCS-27974 | 594882 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | balachandras | 0 |  | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | QA: Testing the throughput with standard/less packet sizes/varied user load in ESP mode
2 | PCS-27972 | 594870 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | balachandras | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | QA:SM HW : ESP Max Users/Tunnel Setup count
3 | PCS-27539 | 593251 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | balachandras | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | Planning to validate RAID and LVM testing
4 | PCS-25735 | 583642 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | balachandras | 75 | 4 | 57600 | 16 | 43200 | 12 | 57600 | 16 | PCS-2122 | PCS-2112 |  | 100% | 0% |  | QA: Testing the HW-RAID controller functionality
5 | PCS-28004 | 594947 | PCS-28042 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06 | May21-ISA8000x-Support | balajit | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | SM HW - ISA8000F Platform Testing, Code Review
6 | PCS-28003 | 594946 | PCS-28042 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06 | May21-ISA8000x-Support | balajit | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | SM HW - ISA8000F Platform addition - License and UI Changes
7 | PCS-28002 | 594945 | PCS-28042 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06 | May21-ISA8000x-Support | balajit | 96 | 6 | 86400 | 24 | 82800 | 23 | 3600 | 1 | PCS-2122 |  |  | 100% | 0% |  | SM HW - ISA8000F Platform addition - Platform changes
8 | PCS-27971 | 594869 | PCS-28017 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06 | May21-Deployment-Phase2 | kalaimani.k | 100 | 4 | 57600 | 16 | 57600 | 16 | 0 | 0 | PCS-2122 |  |  | 100% | 0% |  | SM-HW : ISA8000 - Make Coreboot/init changes as platform specific
9 | PCS-27007 | 590473 | PCS-28017 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06 | May21-Deployment-Phase2 | kalaimani.k | 25 | 8 | 115200 | 32 | 28800 | 8 | 86400 | 24 | PCS-2118 | PCS-2120 | PCS-2122 | 100% | 0% |  | SM-HW: ISA8000 Upgrade and Rollover Confirmation with LVM
10 | PCS-27969 | 594853 | PCS-28017 | 20-05-2021 | 2021-03-06 | 20-05-2021 | 2021-03-06 | May21-Deployment-Phase2 | kalaimani.k | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | LVM: Support and bug fixes
11 | PCS-27566 | 593427 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | karthikr | 0 | 4 | 28800 | 8 | 0 | 0 | 28800 | 8 | PCS-2122 |  |  | 100% | 0% |  | QA: SMHW: Tunnel setup rate test for 25k Users on SSL mode
12 | PCS-27538 | 593250 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | karthikr | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | QA: SM HW : Perform throughput tests with IMIX traffic(SSL)
13 | PCS-27978 | 594893 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | karthikr | 0 | 4 | 57600 | 16 | 0 | 0 | 57600 | 16 | PCS-2122 |  |  | 100% | 0% |  | QA: SM HW : SSL Max Throughput (25k Users/Tunnels, 1350 bytes)
14 | PCS-27975 | 594885 | PCS-28018 | 20-05-2021 | 17-06-2021 | 20-05-2021 | 17-06-2021 | May21-Performance | karthikr | 50 | 2 | 28800 | 8 | 14400 | 4 | 14400 | 4 | PCS-2122 |  |  | 100% | 0% |  | QA: Build image from Build plan

## gen_sheet
s.no | EPIC ID | SPRINT ID | STORY ID | STORY DESCRIPTION | ASSIGNED TO | ESTIMATED STORY POINTS | STORY PLANNED START | STORY PLANNED END | EFFORT CONSUMED (IN HRS) | Time spent (IN Secs) | EFFORT CONSUMED (IN HRS) | PENDING EFFORT (IN HRS) | STORY ACTUAL START | STORY ACTUAL END | STORY Effort completion % | STORY Schedule Progress % | STORY Schedule Overrun % | Remarks
1 | PCS-28018 | PCS-2122 | PCS-27974 | QA: Testing the throughput with standard/less packet sizes/varied user load in ESP mode | balachandras |  | 20-05-2021 | 17-06-2021 | 16 | 57600 | 16 | 16 | 20-05-2021 | 17-06-2021 | 0 | 100% | 0%
2 | PCS-28018 | PCS-2122 | PCS-27972 | QA:SM HW : ESP Max Users/Tunnel Setup count | balachandras | 4 | 20-05-2021 | 17-06-2021 | 16 | 57600 | 16 | 16 | 20-05-2021 | 17-06-2021 | 0 | 100% | 0%
3 | PCS-28018 | PCS-2122 | PCS-27539 | Planning to validate RAID and LVM testing | balachandras | 4 | 20-05-2021 | 17-06-2021 | 16 | 57600 | 16 | 16 | 20-05-2021 | 17-06-2021 | 0 | 100% | 0%
4 | PCS-28018 | PCS-2122 | PCS-25735 | QA: Testing the HW-RAID controller functionality | balachandras | 4 | 20-05-2021 | 17-06-2021 | 16 | 57600 | 16 | 16 | 20-05-2021 | 17-06-2021 | 75 | 100% | 0%
5 | PCS-28042 | PCS-2122 | PCS-28004 | SM HW - ISA8000F Platform Testing, Code Review | balajit | 4 | 20-05-2021 | 2021-03-06 | 16 | 57600 | 16 | 16 | 20-05-2021 | 2021-03-06 | 0 | 100% | 0%
6 | PCS-28042 | PCS-2122 | PCS-28003 | SM HW - ISA8000F Platform addition - License and UI Changes | balajit | 4 | 20-05-2021 | 2021-03-06 | 16 | 57600 | 16 | 16 | 20-05-2021 | 2021-03-06 | 0 | 100% | 0%
7 | PCS-28042 | PCS-2122 | PCS-28002 | SM HW - ISA8000F Platform addition - Platform changes | balajit | 6 | 20-05-2021 | 2021-03-06 | 24 | 86400 | 24 | 1 | 20-05-2021 | 2021-03-06 | 96 | 100% | 0%
8 | PCS-28017 | PCS-2122 | PCS-27971 | SM-HW : ISA8000 - Make Coreboot/init changes as platform specific | kalaimani.k | 4 | 20-05-2021 | 2021-03-06 | 16 | 57600 | 16 | 0 | 20-05-2021 | 2021-03-06 | 100 | 100% | 0%
9 | PCS-28017 | PCS-2118 | PCS-27007 | SM-HW: ISA8000 Upgrade and Rollover Confirmation with LVM | kalaimani.k | 8 | 20-05-2021 | 2021-03-06 | 32 | 115200 | 32 | 24 | 20-05-2021 | 2021-03-06 | 25 | 100% | 0%
10 | PCS-28017 | PCS-2122 | PCS-27969 | LVM: Support and bug fixes | kalaimani.k | 4 | 20-05-2021 | 2021-03-06 | 16 | 57600 | 16 | 16 | 20-05-2021 | 2021-03-06 | 0 | 100% | 0%
11 | PCS-28018 | PCS-2122 | PCS-27566 | QA: SMHW: Tunnel setup rate test for 25k Users on SSL mode | karthikr | 4 | 20-05-2021 | 17-06-2021 | 8 | 28800 | 8 | 8 | 20-05-2021 | 17-06-2021 | 0 | 100% | 0%
12 | PCS-28018 | PCS-2122 | PCS-27538 | QA: SM HW : Perform throughput tests with IMIX traffic(SSL) | karthikr | 4 | 20-05-2021 | 17-06-2021 | 16 | 57600 | 16 | 16 | 20-05-2021 | 17-06-2021 | 0 | 100% | 0%
13 | PCS-28018 | PCS-2122 | PCS-27978 | QA: SM HW : SSL Max Throughput (25k Users/Tunnels, 1350 bytes) | karthikr | 4 | 20-05-2021 | 17-06-2021 | 16 | 57600 | 16 | 16 | 20-05-2021 | 17-06-2021 | 0 | 100% | 0%
14 | PCS-28018 | PCS-2122 | PCS-27975 | QA: Build image from Build plan | karthikr | 2 | 20-05-2021 | 17-06-2021 | 8 | 28800 | 8 | 4 | 20-05-2021 | 17-06-2021 | 50 | 100% | 0%